## Manual Chart
|  |  | October |  | November |  |  |  | December |  |  |  | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  | July
TASK NAME | END DATE | DURATION (weeks) | 2022-10-23 | 2022-10-30 | 2022-11-06 | 2022-11-13 | 2022-11-20 | 2022-11-27 | 2022-12-04 | 2022-12-11 | 2022-12-18 | 2022-12-25 | 2023-01-01 | 2023-01-08 | 2023-01-15 | 2023-01-22 | 2023-01-29 | 2023-02-05 | 2023-02-12 | 2023-02-19 | 2023-02-26 | 2023-03-05 | 2023-03-12 | 2023-03-19 | 2023-03-26 | 2023-04-02 | 2023-04-09 | 2023-04-16 | 2023-04-23 | 2023-04-30 | 2023-05-07 | 2023-05-14 | 2023-05-21 | 2023-05-28 | 2023-06-04 | 2023-06-11 | 2023-06-18 | 2023-06-25 | 2023-07-02 | 2023-07-09 | 2023-07-16 | 2023-07-23 | 2023-07-30
|  |  | W1 | W2 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5
Critical path
review previous work, and rewrite the existing code for improved readability and manageability. | 2022-11-17 | 4 | 2022-10-30: 1; 2022-11-06: 1; 2022-11-13: 1; 2022-11-20: 1; 2023-01-22: exams Period; 2023-04-02: passover; 2023-07-09: Test Period; 2023-07-30: Test Period
Review papers on accelerometers use for noise filtering and feature extraction for EMG data, and on accelerometers use in deep learning. | 2022-12-03 | 3 | 2022-11-13: 1; 2022-11-20: gal not avaivable; 2022-11-27: 1
1
define a new protocol for data collection with a free-hand position and conduct experiments to collect data | 2022-12-26 | 3 | bar: 2022-12-04 to 2022-12-18
explore methods for noise rejection and for separating gestures data from non-gesture data | 2022-01-28 | 4 | bar: 2022-12-11 to 2023-01-01
create new heatmaps/features for the networks | 2023-05-10 | 4 | bar: 2023-04-16 to 2023-05-14
train, test, and optimize a DL network on the new data (for each task) | 2023-06-02 | 4 | bar: 2023-05-07 to 2023-05-28
Floating tasks | bar: 2022-10-23 to 2023-01-15; 2023-03-12 to 2023-03-26; 2023-04-16 to 2023-07-02; 2023-07-23
create a UX & avatar for hand gestures visualization | 2022-11-30 | 2 | bar: 2022-12-04 to 2022-12-11
integrate continuous segmentation (for real-time usage) | 2023-01-16 | 4 | bar: 2022-12-18 to 2023-01-15
explore more models for continuous events classification (RNN etc.) | 2023-04-01 | 3 | bar: 2023-03-12 to 2023-03-26
Course deadlines | bar: 2022-10-23 to 2023-01-15; 2023-03-12 to 2023-03-26; 2023-04-16 to 2023-07-02; 2023-07-23
Gantt chart presentation | 17/11/22 | 2 | bar: 2022-11-06 to 2022-11-13
First Report submission | 22/1/23 | 3 | bar: 2023-01-01 to 2023-01-15
First presentation session | 16-20/4/23 | 2 | bar: 2023-03-19 to 2023-03-26; 2023-04-16
Abstract submission | 13/6/23 | 1 | bar: 2023-06-04 to 2023-06-11
Project day (defence and posters) | 20/6/23 | 3 | bar: 2023-06-04 to 2023-06-18
Final report submission | 31/7/22 | 6 | bar: 2023-06-04 to 2023-07-02; 2023-07-23